## Sheet1
Conestoga College
Team: | Michael Stacey, Swagat Samal, Puneet Chopra, Shubham Singh
Release Plan Summary
|  | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: Jan-23 | Due: Feb-13 | Due: Mar-13 | Due: Apr-3 | Due: Apr-24
# | Feature / Requirement
1 | Project Charter | 2
2 | Team Charter | 2
3 | Design User Registration Page |  | 4
4 | Implement Email Verification |  | 4
5 | Design Login Page |  | 4
6 | UML Diagrams |  | 6
7 | Agile Iteration plan |  | 4
8 | Database design |  |  | 6
9 | Design Mock Data |  |  | 6
10 | Wireframe and Prototyping |  |  | 8
11 | Entity Relationship Diagram |  |  | 4
12 | Implement Place order |  |  |  | 6
13 | Design Landing Page |  |  |  | 8
14 | Implement Order Confirmation |  |  |  | 4
15 | Implement fake payment page |  |  |  | 6
16 | Unit Test and result |  |  |  | 10
17 | Working code demo |  |  |  | 2
18 | Transition/Code documentation |  |  |  |  | 16
19 | Implement Logger |  |  |  |  | 16
| Work Effort in Person Days (PD) | 4 | 22 | 24 | 36 | 32 | 118 | Target: 135 to 150 PD for team of 3
Given: 1 PD = 4 hours
Estimate: 3 PD per week = 45 PD per member; 135 PD for team of 3