## Sheet1
Conestoga College
Team: | Student A, Student B
Agile Product Feature List - Backlog Template
# | Description | PD est. | By | Note: PD = Person day = 4 hours; start feature # from 101 (reserve 1-100 for other requirements)
| High Priority |  |  | Note: Only high priority items are prioritized, assigned to iteration, and estimated
Iteration 1
3 | Design User Registration Page |  | 4
5 | Design Login Page |  | 4
Iteration 2
8 | Database design |  |  | 6
10 | Wireframe and Prototyping |  |  | 8
Iteration 3
12 | Implement Place order |  |  |  | 6
13 | Design Landing Page |  |  |  | 8
16 | Unit Test and result |  |  |  | 10
| Medium Priority |  |  | Note: Medium and Low are prioritized but not yet assigned to iteration, nor estimated
Iteration 1
4 | Implement Email Verification |  | 4
7 | Agile Iteration plan |  | 4
Iteration 2
11 | Entity Relationship Diagram |  |  | 4
Iteration 3
14 | Implement Order Confirmation |  |  |  | 4
15 | Implement fake payment page |  |  |  | 6
17 | Working code demo |  |  |  | 2
Low Priority
Iteration 1
6 | UML Diagrams |  | 6
Iteration 2
9 | Design Mock Data |  |  | 6
Iteration 3
17 | Working code demo |  |  |  | 2
19 | Implement Logger |  |  |  |  | 16