## Sheet1
Conestoga College
Team: | Swagat Samal, Shubham Singh, Puneet Chopra
Agile Product Feature List - Backlog Template
# | Description | PD est. | By | Note: PD = Person day = 4 hours; start feature # from 101 (reserve 1-100 for other requirements)
| High Priority |  |  | Note: Only high priority items are prioritized, assigned to iteration, and estimated
Iteration 1
101 | Use case diagram | 1 | SS
102 | Project setup | 2 | SS
103 | Analysis Level Class Diagram | 1 | PC
104 | System Sequence Diagram | 1 | PC
105 | State Chart Diagram | 1 | SS
106 | Design login page | 2 | PC
107 | Design Registration page | 2 | SS
108 | Email Validation for registration | 3 | SS
109 | Design Database | 4 | SS
Iteration 2
110 | Class Diagram | 1 | SS
111 | Data Dictionary | 1 | SS
112 | Entity Relation Diagram | 1 | PC
113 | Navigation Diagram | 1 | PC
114 | Sequence Diagram | 1 | SS
115 | Application Prototype | 5 | SS
Iteration 3
116 | User Profile Page | 3 | SS
117 | Subsciption Page | 7 | SS
118 | Manage Post Content | 4 | PC
119 | Post Hobby | 3 | SS
120 | Database integeration | 6 | PC
121 | User Account Settings Page | 7 | SS
| Medium Priority |  | SS | Note: Medium and Low are prioritized but not yet assigned to iteration, nor estimated
122 | Unit Testing of application | 2 | SS
123 | Bug Fixes | 3 | SS
Low Priority
124 | Web Application Styling Review | 3 | PC
125 | Populating Application with meaningful related data | 1 | SS