## Sheet1
Conestoga College
Team: | Swagat Samal, Shubham Singh, Puneet Chopra
Release Plan Summary
|  | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: Jan-23 | Due: Feb-13 | Due: Mar-13 | Due: Apr-3 | Due: Apr-24
# | Feature / Requirement
1 | Project Vision statement | 4
| Market Research | 5
| Application Template | 5
110 | Project Setup |  | 3
101 | Database Design |  | 4
| Login Page Design |  | 7
| Registration Page Design |  | 6
| Application Flow |  | 5
| Email Validation |  | 3
107 | Application Prototype |  |  | 8
109 | UI implemented for Login page |  |  | 6
| UI implemented for Registration page |  |  | 6
| UI implemented for Home Page |  |  | 7
| Application Design template |  |  |  | 6
| Meaningfull Datat populated to application |  |  |  | 5
| Bugs fixes |  |  |  | 5
| Application UI Completed |  |  |  | 9
| Application Payment/Subcription plan decided |  |  |  | 8
| Implemented User Profile Page |  |  |  |  | 6
| Implemented Subscription page |  |  |  |  | 8
| Implemented Post hobby feature |  |  |  |  | 7
| Implemented Database integeration |  |  |  |  | 9
| Implemented My Account Feature |  |  |  |  | 9
| Implemented Author Profile page |  |  |  |  | 8
| Work Effort in Person Days (PD) | 14 | 28 | 27 | 33 | 47 | 149 | Target: 135 to 150 PD for team of 3
Given: 1 PD = 4 hours
Estimate: 3 PD per week = 45 PD per member; 135 PD for team of 3